## Sheet1
Purpose of website: Coffee Fan Page to be created by 31.01.21 Outcome of project: Completed Website
Purpose of website: Coffee Fan Page Outcome of project: Completed Website
| Days 1 | Days 2 | Days 3 | Days 4 | Days 5 | Days 6 | Days 7 | Days 8 | Days 9 | Days 10 | Days 11 | Days 12 | Days 13 | Days 14 | Days 15 | Days 16 | Days 17 | Days 18 | Days 19 | Days 20 | Days 21
Produce website concept | bar: Days 1
Research similar websites for gaps in content | bar: Days 1
Wire diagrams of web pages | bar: Days 1 to Days 3
Produce story board for web pages | bar: Days 4 to Days 6
Source copy right free images for web site | bar: Days 7 to Days 8
Set up file for website content | bar: Days 7 to Days 8
Produce text for web pages | bar: Days 9 to Days 11
Crop and filter images for web pages | bar: Days 9 to Days 11
Produce style for content | bar: Days 12 to Days 14
Add content to web pges with consistent look and feel | bar: Days 15 to Days 17
Produce navigation for web pges | bar: Days 17
Check web pages to functionality | bar: Days 18
Check markup | bar: Days 18
Check css | bar: Days 18
Test website | bar: Days 18
Research potential for advertising on the site | bar: Days 19
Upload to hosting website | bar: Days 20
Test website | bar: Days 20 to Days 21